## Tabelle1(02-09)
No | Description | Possibility |  | Agreement | Fixed
1 | Switch the Logo to the Quickpen Logo in the header | Possible |  |  | Fixed
2 | The URL is sometimes pointing to the Godaddy Website, is quickpen.ai, www.quickpen.ai, http://quickpen.ai, http://www.quickpen.ai all connected properly? | Possible | This is DevOps role. |  | Fixed
3 | Add SSL certificate to the website | Possible | You should buy a certificate for SSL https://www.godaddy.com/web-security/ssl-certificate
4 | If you click on the Get Started Button nothing happens | You must logined to the site. I will update the site. Move the login page when user click get started button.
5 | The site takes quite some time to load, can the loadtime be improved? Can the site be loaded directly without the need for the quickpen logo and the loading bar? The same goes for the loading time for the rephrase functionality, can the performance be improved for faster loading / results? | Possible. | I will solve this problem as DevOps position. I used for this AWS Cloud Formation and EC2 Load Balencer. |  | Fixed
6 | If you click on the rephrase icon without marking the text nothing happens, it should auto-detect the cursor/text position and rephrase the current sentence. | Possible
7 | If you click on the rephrase icon and want to paste the result by clicking on the icon next to the rephrased text, the text is not copied as a result. The icon has no function | in order to replace the text, you should click the item, not icon button. The function of icon button, is to copy the sentence on clipboard. You can page it using Ctrl + V.
8 | Add Undo, Redo, Copy All Function | Possible | we should set a new milestone for this function.
9 | Add Word Count in the bottom left corner | Possible
10 | Write the text "Rephrase" directly under the icon, instead of a mouse over hover, the same goes for the Paragraph, Article, and Plagirism Function, You can add the Citation function in the header as well | I will check and fix it.
11 | Adjust the font and the font size to match that of easyessay.ai | I will try it
12 | If you use the website on mobile, it zooms in when you write the text, it should not do that. | I will check and fix it.